## Feasibility Study
Feasibility Study – Student Tutoring Matchmaking System
Web/mobile platform that matches students with suitable tutors based on subject, level, availability and ratings, and manages booking, sessions and feedback.
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Students find tutors through word of mouth, social-media groups or notice boards; tutor quality and availability cannot be verified; arranging times by chat is slow. | Web app + mobile app (Android/iOS); database (PostgreSQL); matching algorithm (subject, level, availability, rating); booking calendar and in-app chat; video-call integration; cloud hosting and automatic backup. | Technically feasible
Operational | Students struggle to find the right tutor; tutors have no steady way to reach students; schedule mismatches and no-shows are common; no feedback mechanism. | Student/tutor profiles; smart matching; one-tap session booking; automatic reminders; ratings and reviews; admin dashboard to approve tutors and handle complaints. | Operationally feasible
Economic | Costs of development or licensing, cloud hosting, notification and video services, and user support. | Better grades and fewer failed courses; less time wasted searching; extra income for tutors; low running cost; optional small commission per session to sustain the system. | Cost-effective
Legal | The platform stores personal data (some students may be minors) and may handle payments; data-protection rules must be followed. | Terms and consent screens (parental consent for minors); encryption in transit and at rest; role-based access; tutor identity verification; secure payment gateway; code of conduct and report/block tools. | Legally feasible
Schedule | Searching for tutors and arranging sessions manually is slow and cannot scale across the college. | Estimated timeline 3–5 months (requirements → design → development → testing → pilot → deployment). | Achievable timeline

## Cost-Benefit Analysis
Cost–Benefit Analysis – Student Tutoring Matchmaking System
Category | Description | Min Cost ($) | Max Cost ($) | Benefits | Estimated Value per Year ($)
Software | Development (in-house) or purchase of platform license; matching engine and booking module | 3000 | 8000 | Automated matching saves students the time spent searching for tutors. | 4000
Hardware / Cloud | Cloud server, database, file storage and backups; video-conferencing API | 1200 | 3000 | Reliable 24/7 access; online sessions without needing physical rooms. | 2000
Notifications | Push/SMS/email gateway fees for booking confirmations and session reminders | 300 | 800 | Timely reminders reduce no-shows and missed sessions. | 1500
Training | Short guides and sessions for students, tutors and administrators | 300 | 800 | Smooth adoption and correct use of the system. | 1000
Maintenance | Annual updates, bug fixes, hosting, security patches, user support | 900 | 1800 | Keeps the system reliable and secure. | 2000
Administration | Current manual process (notice boards, group chats, spreadsheets for pairing students and tutors) | 0 | 0 | Replaced by automated matching, booking records and reports. | 1500
Student Outcomes | Students without tutoring support struggle in difficult courses, fail or drop out | 0 | 0 | Higher grades, fewer failures, better satisfaction and income for peer tutors. | Intangible but high value
Total |  | 5700 | 14400 |  | 12000
Summary
Total Estimated Costs (first year) |  | $5,700 – $14,400
Total Estimated Annual Benefits/Savings |  | $12,000+
Net Benefit – Year 1 (benefits minus average cost) |  | 1950